Annex 1:  ICR 2015-2018 HR Excellence in Research Action Plan – Updated December 2016

| 2014-2018 ICR Action plan |  |
| --- | --- |
|  | Action | Owner(s) and related action plans | Success Measure | Update October 2016 |
| Using data to inform priorities and measure impact |  |
| 1a | Run Staff Survey annually Concordat principle 7 | Head of OD | i) Staff data analysed annually to monitor trends. Annually in May. | i)Complete- Staff data run and analysed in 2014 and 2015 with record response rates of 62% and 79%.The survey will not be repeated until 2017 to avoid survey fatigue |
| 1b | Separate survey data out for research versus non-research staff, and further analysis for divisions and different staff groups (postdocs, team leaders and other research staff). Feed in to Athena SWAN groups, staff/student associations and benchmark to CROS/PIRLS. Concordat principle 7 | Head of OD, RDC, ASC | i)Divisional data provided to all team leaders – by December 2014. Discuss gender-related differences with divisional Athena SWAN reps and identify local issues to address and organisation issues to be raised at ASSSG by March 2015. ii)Analysis for research staff only, internal news article to publicise results – by February 2015. iii)Staff group data provided to staff associations – by Feb 2015. | i)Complete. Data included in successful Athena SWAN Silver Award submission in 2016 with action plan to address issues identified ii) Complete - Research-specific data analysed and publicised to relevant groups e.g. Postdoc Association and SO Association, Clinicians network. iii)Complete - Staff group data provided to Staff Associations and Staff Engagement Committee are progressing the action plan |
| 1c | Improved recruitment data Improve transparency of recruitment of team leaders: Investigate how search committees identify potential CDF on occasion that open advertisement is not used Review appointment procedure for Heads of Division Concordat principles 1, 6 | HR Director HR IO Action plan: ASSSG | i) Team leaders reminded to complete eRecruitment shortlist data by HR IO for every recruitment campaign. Mandatory eRecruitment training to support this embedded in to manager induction (developed by January 2015). ii)Policy for senior recruitment developed to include guidance on how CDF appointments are made and division heads appointed - by March 2015. | i) Mandatory training embedded in manager induction but delays in training on shortlisting due to delays in purchasing and installing software update. This will be in place in Q1 2017 when we will start monitoring % managers using the shortlisting module and enable target rates to be set ii) Complete -Policy for senior staff recruitment developed and approved including guidance on CDF and Division Head appointments, This has improved transparency and monitoring of applicants and fed into our Athena SWAN Silver award. Gender balance of applicants reported quarterly to Management Executive including success rate. A review of shortlisting processes in senior recruitment will be undertaken in 2017 and expanded to include all staff appointments once the new e-recruitment module is implemented than that data becomes available. |
| 1d | Establish the career destinations of former researchers (postdocs, students, technical staff) Concordat principles 3, 4 | RDA, Head of Registry, RDC Action plan: HR Strategy | i) Present initial findings at postdoc careers conference December 2014. ii)Promote the LinkedIN online platform at postdoc events and include link in exit questionnaire for leavers – implemented in February 2015. iii) Increase the next destination data from 57% to 75% of postdoc leavers and publish a summary. June 2015. | i)Completed for Postdocs and students – findings shared with ICR management executive as well as with ‘careers advisors who support researchers’ network (London, Oxford & Cambridge) and internationally at Stanford, UCLA and Scripps institute. Postdoc careers data presented at Vitae and HEFCE workshops. ii) Complete LinkedIn group established with 134 members. These are used as a source of speakers for a range of events including the postdoc careers conference iii) Complete – next destination data gathered for 82%. Summary of this has been published and presented to Vitae. ECU and HEFCE as example of innovative practice |
| 1e | Explore how to measure the impact of ICR-provided training/careers support on the careers of those who left ICR Concordat principles 3, 4 | RDA, RDC | i) Propose a survey for alumni and establish a means to distribute it to network. November 2015. Use results to inform ongoing researcher development programme. | i)Ongoing – survey has been designed and will be piloted with the postdoc alumni group and results reported to Athena SWAN Steering Committee by April 2017 |
| 2) Leadership and management development |  |
| 2a | Mandatory equality and recruitment training: Increase attendance of current staff on Equality Excellence training through improved monitoring at probation review point. New recruitment training developed and offered to all panel chairs by May 2015. Concordat principles 1, 6 | Head of OD Action plan: ASSSG | i) 80% current staff to have attended Equality training by December 2015. ii) Recruitment training delivered to 60% of panel chairs by December 2015. | i) Delayed/Ongoing – currently 71% of staff have attended the training. This is increasing as it now a condition of new starters completing their probation and HR audit completion before signing off probation ii) Delayed/Ongoing – currently 46% of target audience have completed. This is below target due to delays in implementing new e-recruitment system. HR to promote once new system in place in early 2017 (see action 1c) |
| 2b | Expand the portfolio of support provided to new team leaders via the established CDF network, providing bite-sized masterclasses on key skills (e.g. supervision skills) to build engagement of the group and involving senior faculty in delivering these. Concordat Principle 1, 2, 4, 5 | Head of OD, CDF network Action plan: ASSSG | i) Deliver 4 bitesize workshops or webinars per year for CDF – evaluate December 2015. ii) Improved results in survey for team leader category against “I am given good training to perform in my current job” – 2016 survey results and reviewed annually over next 4 years. iii)Monitor progression of CDF to tenured faculty to achieve 80% success between 2014-2018. | i) Complete - Workshops provided on grant applications, influencing, employment law, recruitment essentials. Staff development, strategy development, and new one due on Clinical Trials. Programmes involved range of senior Faculty including Chief Executive, Research Director as well as Heads of Research Operations and HR. Programme content and impact discussed at annual CDF away-days ii) Ongoing – Question not asked in 2015 (abridged) survey so comparator not yet available but will be included in 2017 survey. iii)Ongoing. The majority of reviews are due 2018/9. To date, one person (successful) has undergone final tenure review |
| 2c | Faculty level mentors provided to all CDF (in addition to their division head) Concordat Principle 1, 2, 4, 5 | Head of OD, Director of Academic Services | i) Mentoring matches made, individuals informed and a best practice briefing offered. By March 2015. | i) Complete. Mentors provided to all CDF and training/ online briefings provided to all. Evaluation of scheme currently underway and will be complete by December 2016 |
| 2d | Improve transparency of promotions criteria for researchers by publicising guidelines and discussing with staff/student research associations. Concordat Principle 2, 5, 6 | HR Director | i) 50% positive response from researchers in Staff Survey (“Promotions criteria are fair and transparent) by 2016. | i) Complete 56% of respondents (2015 survey) report promotions criteria are fair and transparent. Faculty recruitment procedures revised and now available on intranet and data on research staff career paths published. SO mentoring scheme publicised at annual SO conference |
| 2e | Supporting females aiming for or in leadership roles i)Evaluate the first cohort of attendees at the Aurora women’s leadership programme ii)Deliver bespoke leadership training to female team leaders e.g. Personal Effectiveness and Power workshop. iii)Ensure selection on to influential senior committees is transparent and fair Concordat Principle 1, 2, 4, 5 | RDA, ASC, ASSSG Chair, ACS Action plan: ASSSG | i.a)Aurora feedback from attendees evaluated and long-term tracking of careers of those who attended via LinkedIN. Initial evaluation of programme by September 2015. i.b)Alternative leadership training options provided to unsuccessful Aurora applicants by March 2015. ii)Roffey Park Personal Effectiveness and Power workshop provided for ICR and RMH female leaders (by June 2015). iii)Guidance on selection of researchers for senior committees developed by ACS by June 2016 | i)Complete - with very positive feedback as to impact on individuals and careers with the proportion of promotions and new career opportunities higher for attendees than non-attendees. Continued biennial monitoring of past cohorts. ii) Complete - Launched the Future Female Leaders programme which has now run twice and 90 % of participants would recommend it to a colleague ii)Complete - positive feedback, 83% attendees said the session was relevant to their role iii) Complete -Committee places are now advertised biannually with interested parties encouraged to attend meetings at observers before committing. Exceptions made for places which depend upon roles e.g. Research Director or CEO which are not advertised. Membership of committees discussed as part of annual appraisal. Proportion of senior committee posts held by women increased significantly from 22% in 2012 to 44% at present. |
| 2f | Establish a new managers network Concordat principle 1, 2, 3, 4 | RDA, Head of OD | i) Attendance and feedback from those groups. We will monitor trends in the staff survey under category “My manager”. Review after 12 months (May 2016). | i) Delayed/Incomplete –A list of relevant managers for this network has been gathered with the initial meeting planned for Feb 2017 |
| 2g | Supporting postdocs aiming for leadership: Run second Pathway to Independence, revised content based on feedback from pilot Offer six places for Leadership in action in collaboration with UCL Concordat principle 1, 2, 3 4, 5 | RDA, Academic Dean Action plan: ASSSG | i) Feedback, continued monitoring of careers of attendees, better-prepared future team leaders. ii) Run Pathways programme June 2015. Monitor career progress of attendees via LinkedIN (ongoing). iii) Leadership in Action run in collaboration with UCL in June 2015. iv)Proposals for additional mentoring and careers support for postdoctoral fellowship holders drafted and presented to Athena SWAN silver group by March 2015 | i) Complete - Feedback presented at Vitae national leadership conference and at Science of Team Science conference in USA (2016) ii)Complete Dedicated LinkedIn group formed for alumni and follow-up events held for 2013 and 2015 cohorts. iii)Complete – ICR has sent 9 researchers to 2 of these events and now have an ongoing collaboration with UCL – feedback has been extremely positive iv) Ongoing – pilot mentoring event run in cancer therapeutics summer 2016 with 21 students/postdocs and 5 team leaders. To be evaluated before trialling in other divisions. |
| 3) Defining career paths and supporting career development |  |
| 3a | Postdoc code of practice disseminated to all new postdocs and to all faculty Concordat principle 2, 3, 4, 5 | RDA, HR Operations teams, HR IO, faculty | Embedded in to eRecruitment process, contract packs and appraisal documentation. February 2015. | Complete Included in every postdoc vacancy since 2015, |
| 3b | Ensure 70% of research staff are aware of access to impartial careers advice Concordat principle 2, 3 | RDA, RDC | Analyse 2014 staff survey responses for researchers versus non-research staff. Achieve at least 70% positive response from researchers in 2015 survey. | Ongoing - In 2014 divisional results for this question vary between 38-66% of research staff reported they were able to access independent careers advice. In 2016 we revised the careers webpages and wording of the sessions offered to highlight that they are available to all researchers – not just students. In addition dedicated careers advice appointments are now at the Scientific Officer and Postdoc Conferences. This question will be re-measured in the 2017 survey |
| 3c | Map clinical academic career paths and present to CRCDWG for discussion/recommendations Concordat principle 1, 4 | RDA, HR Director, HoCS Action plan: ASSSG | Career paths mapped and document presented to CRCDWG. October 2015. | Completed and used as basis for clinician development programmes |
| 3d | Conduct a gap analysis on the career development available to clinical academics and develop proposals for further support Concordat principles 3,4 | RDA, ASSSG, CRCDWG Chair Action plan: ASSSG | i) Actions agreed by April 2015. Ongoing monitoring by appropriate groups. ii) Explore options for a clinician leadership programme based on Pathway to Independence model and agree content with CRCDWG – May 2015 | i)Complete – recommendations implemented include mentoring and a dedicated clinical academic career development programme which have been featured as a case study by Vitae ii)Completed Clinical version of the programme agreed and delivered in Nov 2016 with partners across BRC network and Cancer Research UK with excellent initial feedback |
| 3e | Establish a mentoring scheme for clinical academics Concordat principles 4, 5, 6 | ASC, Deputy Director of BRC, Action plan: ASSSG. | Mentors identified and offered to clinical academics routinely. December 2015. | Complete Piloted with female clinicians and research active consultants. Both mentors and mentees were provided with training. 13 pairs matched to date. Independent external evaluation of pilot currently underway with final report due March 2017 (1 year after scheme was initiated) |
| 3f | Develop and pilot an introduction to bioinformatics programme and ensure relevant staff and students are aware of all related support, internally and externally. Concordat principles 3, 4 | RDC, faculty champion, SCUF Action plan: SSTR | Pilot introduction course and evaluate by September 2015. Create a specific training page to signpost support for researchers in scientific computing/bioinformatics by February 2016. Review whole bioinformatics support programme January 2017. | Complete Introductory programme delivered with excellent feedback and was subsequently repeated |
| 3g | Early training needs screening tool developed for students to complete during induction week. Concordat principles 4, 5 | Asst Dir (AR) Action plan: SSTR | Pilot in 2014/5 and roll out for 2015/6 starters | Complete - 51% of 2015/16 starters are accessing the new screening tool in addition to having an inital training needs discussion with their supervisor. 90% of those who logged in to the tool completed the process to automatically populate their PDP. This year students who have not logged in to the tool will be sent follow up emails to encourage them to do so. It will also be implemented for the MDRes students. |
| 3h | Supporting training in project risk: Identify training tools for project risk management Amend guidance and Codes to state that project risk must be covered in first year report and 2.5 year report. Concordat principles 3 | RDC RDPEM Action plan: SSTR | Project risk considered by all students and described/discussed in first year and 2.5 year reports. March 2015 June 2015 | Complete - resource developed and referenced in the student codes of practice relating to their 1st and 2.5 year reports and monitored through regular student supervision meetings. |

Glossary

ASSSG – Athena SWAN Silver Steering Group

ACS – Assistant company secretary

ASC – Athena SWAN coordinator

BRC – Biomedical Research Centre

CRCDWG – Clinical Research Career Development Working Group

Head of OD – Head of Organisational Development

HoCS – Head of Clinical Studies

HR IO - HR Information Officer

HR OPS – HR Operations Manager

RDA/RDM – Researcher Development Advisor/Manager (Role name changed)

RDC – Researcher Development Coordinator

RDPEM – Research Degrees Programme and Events Manager

SCUF – Scientific Computer Users Forum

SO – Scientific Officer

SSTR – Strategic Student Training Review (Triennial)